## RAR
6Th RAR
हिन्दुस्तान एरोनॉटिक्स लिमिटेड/ Hindustan Aeronautics Limited
इंजन प्रभाग-कोरापुट/ Engine Division-Koraput
संयंत्र इंजीनिय़री बिभाग/ Plant Engineering Department
कार्य का नाम/Name of work: |  |  | Annual Maintenance Contract of 360 Nos of machine tools,equipments in Bl-3A and Bl-4.
कार्यादेश सं/ Work Order No/Contract No:/Date: |  |  | KPT/SNC/21SNCAT-522,Dt 16/08/2022 | [7 empty] | Dt: | 11-03-2024
ठेके दार का नाम/ Name of the Contract Agency: |  |  | M/s. UMA ENGINEERS, SUNABEDA-2
(period from Dt.10-11-2023 to Dt.09-02-2024)
Sl.No | कार्य वीवरण/Description of work | आदेशनुसार/ As per Order |  |  |  | निस्पादनुसार/As per Execution |  |  | पिछले बिल की कटौती Deduct last bill |  | वर्तमान भुगतान/Present Payment
|  | मात्रा/Qty | इकाई/Unit | दर/Rate | राशि/Amount | निष्पादित मात्रा/ Qty Executed | स्विकृत हुई मात्रा/Qty Passed | राशि/Amount Executed | मात्रा/Qty | राशि/Amount | मात्रा/Qty | राशि/Amount
1 | Breakdown maintenance of 194 Nos of Small capacity machines in Block-3A & Block-4.Qty :194 Nos x 24 months | 4656 | Nos | 245 | 1140720 | 3492 | 3492 | 855540 | 2910 | 712950 | 582 | 142590
2 | Breakdown maintenance of 135 Nos. of medium capacity mahcines in Block-3A & Block-4. Qty : 135 Nosx 24 months | 3240 | Nos | 300 | 972000 | 2430 | 2430 | 729000 | 2025 | 607500 | 405 | 121500
3 | Breakdown maintenance of 31 Nos. of heavy capacity mahcines in Block-3A & Block-4. Qty: 31 Nos x 24 Months | 744 | Nos | 440 | 327360 | 558 | 558 | 245520 | 465 | 204600 | 93 | 40920
4 | Monthly Preventive maintenance of 120 Nos. of small capapcity mahcines in Block-3A,Qty: 120Nos X 24 months | 2880 | Nos | 485 | 1396800 | 2160 | 2160 | 1047600 | 1800 | 873000 | 360 | 174600
5 | Monthly Preventive maintenance of 60 Nos. of medium capacity mahcines in Block-3A.Qty: 60Nos X 24 months | 1440 | Nos | 520 | 748800 | 1080 | 1080 | 561600 | 900 | 468000 | 180 | 93600
6 | Monthly Preventive maintenance of 14 Nos. of heavy capacity mahcines in Block-3A.Qty: 14Nos X 24 months | 336 | Nos | 690 | 231840 | 252 | 252 | 173880 | 210 | 144900 | 42 | 28980
7 | Quartley Preventive maintenance of 74 Nos. of small capapcity mahcines in Block-4.Qty: 74 Nos X 8 quarters | 592 | Nos | 690 | 408480 | 444 | 444 | 306360 | 370 | 255300 | 74 | 51060
8 | Quarterly Preventive maintenance of 75 Nos. of medium capacity mahcines in Block-4..Qty: 75 Nos X 8 quarters | 600 | Nos | 800 | 480000 | 450 | 450 | 360000 | 375 | 300000 | 75 | 60000
9 | Quarterly Preventive maintenance of 17 Nos. of heavy capacity mahcines in Block-4..Qty: 17 Nos X 8 quarters | 136 | Nos | 900 | 122400 | 102 | 102 | 91800 | 85 | 76500 | 17 | 15300
| Total |  |  |  | 5828400 |  |  | 4371300 |  | 3642750 |  | 728550
| GST@18% |  |  |  | 1049112 |  |  | 786834 |  | 655695 |  | 131139
| Grand Total |  |  |  | 6877512 |  |  | 5158134 |  | 4298445 |  | 859689
| Prepared & Checked by |  |  |  |  | Recommended & Approved by
| V. MADHU |  |  |  |  | P K PANDA
| Manager (Maint.) |  |  |  |  | Ch Manager(Maint.)

## Payment Recommendation
PAYMENT RECOMMENDATION |  |  | W.O issued on | 2017-12-22
I | कार्यदेश का मूल्य/Cost of work as per Work Order-----KPT/SNC/21SNCAT-522,Dt 16/08/2022 |  | Transit period | 2018-01-21
II | ठेकेदार द्यारा संपादित कार्य का मूल्य/Cost of work executed by the contractor----. |  | Agreement made on | 2018-01-03
III | अंतिम भुगतान/Payment made in last RARs ---------- |  | BG deposited on | 2018-01-01
IV | कम्: चालु खाता प्रेषण से प्रतिधारण राशि रखा गया/Less:- Keep back towards retention money from the bill
V | सामिल: अंतिम चालु खाता प्रेषण से प्रतिधारण राशि का वापसि/Add:- Released of retention money from last RAR bill | 0
VI | मेसिन ठप एवं अनुरक्षण निवारण खिलाप के लिए जुरमाना /Less: Penalty towards Break down and Preventive maintenance (Attached) | 123456 |  | Retemtion money details
VII | Penalty towards submission of agreement (3 weeks delay and penalty of Rs.2500/- per week) | 0
VIII | ठेकेदार पक्ष में दित्यिय चालु खाता प्रेषण भुगतान के लिए बंदबस्त का सिफारिश/ Present payment recommended in favour of the contractor in settlement of RAR-6 I.e. (II-III-IV+V-VI) |  | RAR | Keep back | Released
| Final Amount (Rs.) |  | 1st | 36642.186
| Rupees six lakh, ninety-three thousand, two hundred and forty-eight point five fivepaisa only |  | 2nd | 40578.143 | 36642.186
| Certified that the contractor M/s UMA ENGINEERS. SUNABEDA-2 has satisfactorily executed the work and the work has been accepted by HAL, being found in line with work order terms and conditions. Hence the payment of Rs.693248.55 is recommended in favour of the contractor in settlement of RAR-6 . It is further certified that there is no other recovery due from the contractor in connection with execution of this work. |  | 3rd | 38061.49 | 40578.143
|  | Approved by | 4th | 38032.42 | 38061.49
|  | P K PANDA | 5th | 42285.62 | 38032.42
| उप महा प्रबंधक(अनुरक्षण) | DGM(MAINT.) | 6th | 37672.64 | 42285.62
|  |  | 7th |  | 37672.64
PAYMENT RECOMMENDATION |  |  | 8th
I
II
III
IV
V
VI
VIII | penalty towards late submission of amendment to contract agreement
VII