## RAR
4th RAR
हिन्दुस्तान एरोनॉटिक्स लिमिटेड/ Hindustan Aeronautics Limited
इंजन प्रभाग-कोरापुट/ Engine Division-Koraput
संयंत्र इंजीनिय़री बिभाग/ Plant Engineering Department
कार्य का नाम/Name of work: |  |  | Annual Maintenance Contract of 360 Nos of machine tools,equipments in Bl-3A and Bl-4.
कार्यादेश सं/ Work Order No/Contract No:/Date: |  |  | KPT/SNC/21SNCAT-522,Dt 16/08/2022 | [7 empty] | Dt: | 2023-08-17
ठेके दार का नाम/ Name of the Contract Agency: |  |  | M/s. UMA ENGINEERS, SUNABEDA-2
(period from Dt.10/05/2023 to Dt.09/08/2023)
Sl.No | कार्य वीवरण/Description of work | आदेशनुसार/ As per Order |  |  |  | निस्पादनुसार/As per Execution |  |  | पिछले बिल की कटौती Deduct last bill |  | वर्तमान भुगतान/Present Payment
|  | मात्रा/Qty | इकाई/Unit | दर/Rate | राशि/Amount | निष्पादित मात्रा/ Qty Executed | स्विकृत हुई मात्रा/Qty Passed | राशि/Amount Executed | मात्रा/Qty | राशि/Amount | मात्रा/Qty | राशि/Amount
1 | Breakdown maintenance of 194 Nos of Small capacity machines in Block-3A & Block-4.Qty :194 Nos x 24 months | 4656 | Nos | 245 | 1140720 | 2328 | 2328 | 570360 | 1746 | 427770 | 582 | 142590
2 | Breakdown maintenance of 135 Nos. of medium capacity mahcines in Block-3A & Block-4. Qty : 135 Nosx 24 months | 3240 | Nos | 300 | 972000 | 1620 | 1620 | 486000 | 1215 | 364500 | 405 | 121500
3 | Breakdown maintenance of 31 Nos. of heavy capacity mahcines in Block-3A & Block-4. Qty: 31 Nos x 24 Months | 744 | Nos | 440 | 327360 | 372 | 372 | 163680 | 279 | 122760 | 93 | 40920
4 | Monthly Preventive maintenance of 120 Nos. of small capapcity mahcines in Block-3A,Qty: 120Nos X 24 months | 2880 | Nos | 485 | 1396800 | 1440 | 1440 | 698400 | 1080 | 523800 | 360 | 174600
5 | Monthly Preventive maintenance of 60 Nos. of medium capacity mahcines in Block-3A.Qty: 60Nos X 24 months | 1440 | Nos | 520 | 748800 | 720 | 720 | 374400 | 540 | 280800 | 180 | 93600
6 | Monthly Preventive maintenance of 14 Nos. of heavy capacity mahcines in Block-3A.Qty: 14Nos X 24 months | 336 | Nos | 690 | 231840 | 168 | 168 | 115920 | 126 | 86940 | 42 | 28980
7 | Quartley Preventive maintenance of 74 Nos. of small capapcity mahcines in Block-4.Qty: 74 Nos X 8 quarters | 592 | Nos | 690 | 408480 | 296 | 296 | 204240 | 222 | 153180 | 74 | 51060
8 | Quarterly Preventive maintenance of 75 Nos. of medium capacity mahcines in Block-4..Qty: 75 Nos X 8 quarters | 600 | Nos | 800 | 480000 | 300 | 300 | 240000 | 225 | 180000 | 75 | 60000
9 | Quarterly Preventive maintenance of 17 Nos. of heavy capacity mahcines in Block-4..Qty: 17 Nos X 8 quarters | 136 | Nos | 900 | 122400 | 68 | 68 | 61200 | 51 | 45900 | 17 | 15300
| Total |  |  |  | 5828400 |  |  | 2914200 |  | 2185650 |  | 728550
| GST@18% |  |  |  | 1049112 |  |  | 524556 |  | 393417 |  | 131139
| Grand Total |  |  |  | 6877512 |  |  | 3438756 |  | 2579067 |  | 859689
| Prepared & Checked by |  |  |  |  | Recommended & Approved by
| V. MADHU |  |  |  |  | P K PANDA
| Manager (Maint.) |  |  |  |  | Ch Manager(Maint.)

## Payment Recommendation
PAYMENT RECOMMENDATION |  |  |  | W.O issued on | 2017-12-22
I | कार्यदेश का मूल्य/Cost of work as per Work Order-----KPT/SNC/21SNCAT-522,Dt 16/08/2022 | 6877512 |  | Transit period | 2018-01-21
II | ठेकेदार द्यारा संपादित कार्य का मूल्य/Cost of work executed by the contractor----. | 3438756 |  | Agreement made on | 2018-01-03
III | अंतिम भुगतान/Payment made in last RARs ---------- | 2579067 |  | BG deposited on | 2018-01-01
IV | कम्: चालु खाता प्रेषण से प्रतिधारण राशि रखा गया/Less:- Keep back towards retention money from the bill | 42984.45 | 859689
V | सामिल: अंतिम चालु खाता प्रेषण से प्रतिधारण राशि का वापसि/Add:- Released of retention money from last RAR bill | 0
VI | मेसिन ठप एवं अनुरक्षण निवारण खिलाप के लिए जुरमाना /Less: Penalty towards Break down and Preventive maintenance (Attached) | 100000 |  |  | Retemtion money details
VII | Penalty towards submission of agreement (3 weeks delay and penalty of Rs.2500/- per week) | 0
VIII | ठेकेदार पक्ष में दित्यिय चालु खाता प्रेषण भुगतान के लिए बंदबस्त का सिफारिश/ Present payment recommended in favour of the contractor in settlement of RAR-? I.e. (II-III-IV+V-VI) | 716704.55 | 716704.55 | RAR | Keep back | Released
| Final Amount (Rs.) | 716704.55 |  | 1st | 36642.186
| Rupees six lakhs seventy nine thousand two hundred twenty nine and fifty five paisa only |  |  | 2nd | 40578.143 | 36642.186
| Certified that the contractor M/s UMA ENGINEERS. SUNABEDA-2 has satisfactorily executed the work and the work has been accepted by HAL, being found in line with work order terms and conditions. Hence the payment of Rs.bill_amount is recommended in favour of the contractor in settlement of RAR-? . It is further certified that there is no other recovery due from the contractor in connection with execution of this work. |  |  | 3rd | 38061.49 | 40578.143
|  | Approved by |  | 4th | 38032.42 | 38061.49
|  | P K PANDA |  | 5th | 42285.62 | 38032.42
| उप महा प्रबंधक(अनुरक्षण) | DGM(MAINT.) |  | 6th | 37672.64 | 42285.62
|  |  |  | 7th | 42984.45 | 37672.64
PAYMENT RECOMMENDATION |  |  |  | 8th
I | कार्यदेश का मूल्य/Cost of work as per Work Order-----KPT/SNC/21SNCAT-522,Dt 16/08/2022 | 6877512
II | ठेकेदार द्यारा संपादित कार्य का मूल्य/Cost of work executed by the contractor----. | 3438756
III | अंतिम भुगतान/Payment made in last RARs ---------- | 2579067
IV | कम्: चालु खाता प्रेषण से प्रतिधारण राशि रखा गया/Less:- Keep back towards retention money from the bill | 42984.45
V | सामिल: अंतिम चालु खाता प्रेषण से प्रतिधारण राशि का वापसि/Add:- Released of retention money from last RAR bill | 0
VI | मेसिन ठप एवं अनुरक्षण निवारण खिलाप के लिए जुरमाना /Less: Penalty towards Break down and Preventive maintenance (Attached) | 100000
VIII | penalty towards late submission of amendment to contract agreement | 0
VII | ठेकेदार पक्ष में दित्यिय चालु खाता प्रेषण भुगतान के लिए बंदबस्त का सिफारिश/ Present payment recommended in favour of the contractor in settlement of RAR-? I.e. (II-III-IV+V-VI) | 716704.55
| Final Amount (Rs.) | 716704.55
Rupees six lakhs seventy nine thousand two hundred twenty nine and fifty five paisa only
Certified that the contractor M/s UMA ENGINEERS. SUNABEDA-2 has satisfactorily executed the work and the work has been accepted by HAL, being found in line with work order terms and conditions. Hence the payment of Rs.bill_amount is recommended in favour of the contractor in settlement of RAR-? . It is further certified that there is no other recovery due from the contractor in connection with execution of this work.
Approved by
P K PANDA
| उप महा प्रबंधक(अनुरक्षण) | DGM(MAINT.)